## Risk Register
Risk ID | Risk Description | Likelihood | Impact | Risk Score | Risk Rating | Mitigation | Owner | Residual Risk | Review Date
R-01 | Cloud data breach due to weak IAM controls | 3 | 3 | 9 | High | Least privilege, MFA, access reviews | Security Lead | Medium | 2026-03-01
R-02 | Credential reuse across SaaS platforms | 3 | 3 | 9 | High | Password policy, MFA, SSO | IT Admin | Medium | 2026-03-01
R-03 | Misconfigured S3 bucket exposing data | 2 | 3 | 6 | Medium | S3 Block Public Access, AWS Config | Cloud Engineer | Low | 2026-03-01
R-04 | Phishing attack leading to account compromise | 3 | 2 | 6 | Medium | Security awareness training | Security Lead | Medium | 2026-03-01
R-05 | Lack of centralized logging & monitoring | 2 | 3 | 6 | Medium | Enable CloudTrail, SIEM | DevOps | Low | 2026-03-01
R-06 | Unpatched cloud workloads | 2 | 3 | 6 | Medium | Patch management program | IT Admin | Low | 2026-03-01
R-07 | Excessive admin privileges | 2 | 3 | 6 | Medium | RBAC enforcement | Security Lead | Low | 2026-03-01
R-08 | No incident response plan | 2 | 3 | 6 | Medium | Create IR plan, tabletop exercises | Management | Medium | 2026-03-01
R-09 | Third-party SaaS vendor security weakness | 2 | 2 | 4 | Medium | Vendor risk assessments | Compliance | Low | 2026-03-01
R-10 | Lack of regular risk assessments | 1 | 3 | 3 | Low | Annual RMF risk assessments | Compliance | Low | 2026-06-01